## Slide 1
Webconférence, le 9 mai 2025
FAIR connexion to EU Water catalogues of water resources
for enhanced innovation with water data
Réunion de lancement

## Slide 2
01
Présentation du projet
02
Point sur les actions en cours
03
Questions diverses

## Slide 3
Présentation du projet
01
Eléments clés
Planning
Présentation des tâches

## Slide 4: Eléments clés du projet
FAIR connexion to EU Water catalogues of water resources for enhanced innovation with water data
Durée : 12 mois
MOA : BRGM
MOE : Data Lime
 Axes forts sur l’expérimentation et l’implication de la communauté
Objectifs :
Recenser les catalogues « eau » en Europe
Tester les capacités Machine2Machine des catalogues
Tester les échanges de données FAIR
Interagir avec la communauté Water4All
Transfert des résultats au BRGM

## Slide 5: Planning prévisionnel
Task | Milestones
Definition of the project frame | 2 weeks after the beginning of the project
Task 1: Listing of EU Metadata catalogues of water resources | throughout the duration of the project 1st iteration
Task 2: Capacity for Machine2Machine exchange identification | From june to december 2025
Task 3: Test for FAIR data exchange | From september 2025 to may 2026
Task 4: Sharing and testing those activities with the Water4All community | throughout the duration of the project 1st iteration
Task 5: Transfer of the solution to BRGM staff | May 2026
Option : Second phase/iteration | May 2026 to December 2027

## Slide 6: Definition of the project frame
Objectives | Set the project frame Validate the methodology Validate the planning |  | 
Terms of intervention | Kick-off meeting |  | 
Deliverables | Meetings minutes | Planning | 2 weeks after the beginning of the 1st iteration

## Slide 7: Task 1 : Listing of EU Metadata catalogues of water resources
Objectives | Collect information on EU metadata catalogues on waters resources Validate the methodology Validate the planning |  | 
Terms of intervention | Define the list of fields to collect Develop a web form based on fields to collect Mobilized the Water4All project community in order to complete the listing Manually complete the listing (iterative logic by country/region) Communicate during event/workshop |  | 
Deliverables | Intermediate listing of EU Metadata catalogues of water resources (50% of the task advancement) Final listing of EU Metadata catalogues of water resources | Planning | throughout the duration of the project 1st iteration

## Slide 8: Task 2: Capacity for Machine2Machine exchange identification
Objectives | Test identified catalogues Machine2Machine capabilities Check compliance of implemented standards (if any) |  | 
Terms of intervention | Identified and Test Machine2Machine capabilities |  | 
Deliverables | Evaluation reports Source codes | Planning | From june to december 2025

## Slide 9: Task 3 : Test for FAIR data exchange
Objectives | Develop prototype for remote Machine2Machine FAIR data exchange Test the prototype with relevant catalogues |  | 
Terms of intervention | Identify candidate catalog for testing Inventory possible solution for FAIR Data exchange Evaluate solution Develop prototype and make exchange test |  | 
Deliverables | Inventory of relevant solutions and products report Intermediate and final version of source code and documentation | Planning | From september 2025 to may 2026

## Slide 10: Task 4 : Sharing and testing those activities with the Water4All community
Objectives | Share and inform the Water4All community |  | 
Terms of intervention | Involvement in Water4all events if needed Document the approach throughout the duration of the project |  | 
Deliverables | 4 Activity reports | Planning | throughout the duration of the project 1st iteration

## Slide 11: Task 5 : Transfer of the solution to BRGM staff
Objectives | Transfer results to BRGM staff |  | 
Terms of intervention | Transfer meeting |  | 
Deliverables | Presentation support | Planning | At the end of the 1st iteration (May 2026)

## Slide 12
Point sur les actions en cours
02
Recensement des catalogues

## Slide 13: Definition of the project frame
Pays : EU 27 + UK
Echelle : National, Regional (Etats Fédéraux), Organisations transfrontalières
Thèmes « Eau » : eaux superficielles continentales et eaux souterraines
Données issues des politiques publiques

## Slide 14: Tâche 1 : Recenser les catalogues « eau » en Europe
Champs à collecter :
    Name of the catalog/repository
    URL
    URL endpoint(s)
    URL doc/model
    Country
    Geographical scale (name of the region or of the water basin)
    Water topics
    Type of repository: simple web page, file download, catalog, API…
    Contact organization
    Contributor name (people who provide the information)
    Keywords in English and in national language (in full text search interface) => websem/thesaurus
Lieu de stockage :
  - GitHub (+ éventuellement GitLab BRGM)
1ères investigations  fichier Excel (google spreadsheet)

## Slide 15: RDV EGM
Sujets : Fiware & Waterverse
Proposition de dates :
  Lundi 12 mai après-midi (sauf entre 16h et 17h)
  Mardi 13 mai après 15h30
  Jeudi 15 mai après 16h
  Mercredi 21 mai après-midi

## Slide 16
Questions diverses
03

## Slide 17: Questions diverses
Validation et Fournitures des pièces administratives
Fourniture du CR
Date du prochain point

## Slide 18
Nicolas DHUYGELAERE
Chef d’entreprise
n.dhuygelaere@gmail.com